1.1.1  AI Certification-to-Course Matching

✔ On Track

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2  |  October 29, 2026

| Status | On Track |
| --- | --- |
| Progress | 55% |
| Lead | Terence Nelson |
| Budget | Included in 2.3 (AI Skills to Course Alignment (V0515)) |
| KPI Current | 117 industry certifications matched |
| 2030 Goal | 0 |
| 2030 Stretch | 0 |
| 25-26 | 117/117 |
| 26-27 | 117/150 |
| 27-28 | 117/0 |
| 28-29 | 117/0 |
| 29-30 | 117/0 |

## Description

The initiative used artificial intelligence to identify potential alignments between industry-recognized certifications and California Community College courses. AI-generated recommendations were subsequently reviewed by faculty participants, whose expertise helped validate, refine, and strengthen the resulting recommendations.
The work is intended to accelerate CPL exploration while preserving local curriculum, policy, and faculty decision-making.

## Latest Update

Date: 2026-10-15

The pilot generated approximately 33,000 proposed credit recommendations across 115 industry certifications, extending Phase 1 work. A 90-day transition of code, database, algorithm, and documentation from EQS to the Foundation/MAP team is underway, with priorities focused on reproducing, securing, and documenting the system before MAP integration and faculty validation.

## Workplan Notes

AI cert-to-course matching Phase 1 complete covering 117 industry certifications in priority sectors. Phase 2 beta expanding certification pool. Production release planned June 2026.

## Milestones

Phase 1 complete: 117 certs covered; June 2026: Phase 2 production release expanding cert pool