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1.1.3  WestEd CPL Scope of Work
↑ In Progress
Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2; Goal 3  |  October 29, 2026
	Status
	In Progress

	Progress
	40%

	Lead
	WestEd (Erin, Kathy, Rajinder)

	Budget
	Included in 1.2 (CPL Credential Registry - WestEd (V0719))

	KPI Current
	6 workstreams active

	2030 Goal
	0

	2030 Stretch
	0

	25-26
	6/4

	26-27
	6/4

	27-28
	6/0

	28-29
	6/0

	29-30
	6/0


Description
Skills taxonomy, credential cataloguing, NFN pilot, student experience mapping, system design, and credential registry expansion planning
Latest Update
Date: 2026-10-15
Phase 1 is complete, and follow-on work has advanced into Credential Registry technical design, governance, user-centered design, and workforce and apprenticeship data integration. Contracting and coordination are progressing among WestEd, the Chancellor's Office, Labor Agency, Credential Engine, Career Passport, and MAP, with current focus on clarifying roles, data requirements, governance, and initial registry experience.
Workplan Notes
WestEd CPL Scope of Work: 6 workstreams active (Credential ID, Course Alignment, NFN Use Case, Student Experience, System Design, Strategic Planning). Skills taxonomy/CTDL work progressing.
Milestones
6 workstreams: Credential ID, Course Alignment, NFN Use Case, Student Experience, System Design, Strategic Planning
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