1.4  California Credential Registry

◎ Foundational Year

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2; Goal 3  |  April 14, 2026

| Status | Foundational Year |
| --- | --- |
| Progress | 15% |
| Lead | Terence Nelson |
| Budget | Included in 1.2 (CPL Credential Registry - WestEd (V0719)) |
| KPI Current | 0 Cumulative credentials published |
| 2030 Goal | 250 |
| 2030 Stretch | 900 |
| 25-26 | 0/0 |
| 26-27 | 0/50 |
| 27-28 | 0/110 |
| 28-29 | 0/175 |
| 29-30 | 0/250 |

## Description

CPL-qualified credentials are hosted on the credential registry.

## Latest Update

Date: 2026-04-07

No credentials published yet; full launch not targeted until 2026-27; schema development underway

## Workplan Notes

No credentials published in registry this period. Full launch not targeted until 2026-27. Standardized credential data schema incorporating TOP and CIP codes is in preparation for the registry pipeline.

## Milestones

2026: Standardized credential data schema with TOP/CIP codes; 2026-27: Registry launch

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | No credentials published yet; full launch not targeted until 2026-27; schema development underway |
| 2026-04-07 | Workplan | No credentials published in registry this period. Full launch not targeted until 2026-27. Standardized credential data schema incorporating TOP and CIP codes is in preparation for the registry pipeline. |
| 2026-03-20 | Progress Update | No credentials published yet; full launch not targeted until 2026-27; schema development underway |