2.1  Statewide Credit Recommendations

✔ On Track

Activity 2: Faculty Workgroups & Credit Recommendations  |  Goal 1  |  April 14, 2026

| Status | On Track |
| --- | --- |
| Progress | 58% |
| Lead | ASCCC / Calvin Klein Gloria |
| Budget | $1,563,900 (ASCCC Pathways to Credit (V0718)) |
| KPI Current | 288 Cumulative credit recommendations |
| 2030 Goal | 1,000 |
| 2030 Stretch | 2,200 |
| 25-26 | 288/200 |
| 26-27 | 288/400 |
| 27-28 | 288/600 |
| 28-29 | 288/800 |
| 29-30 | 288/1,000 |

## Description

Create and adopt statewide CPL credit recommendations through ASCCC faculty workgroups.

## Latest Update

Date: 2026-04-07

288 cumulative credit recommendations; 281 adopted this year; 230 in progress through adoption workflow

## Workplan Notes

288 cumulative statewide credit recommendations with 281 adopted this academic year. 230 currently in progress through college review and adoption workflows. Spanning military, apprenticeship, industry certification, and professional licensure fields.

## Milestones

June 2026: 650+ cumulative adopted recommendations; 2030: 1,000 target

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 288 cumulative credit recommendations; 281 adopted this year; 230 in progress through adoption workflow |
| 2026-04-07 | Workplan | 288 cumulative statewide credit recommendations with 281 adopted this academic year. 230 currently in progress through college review and adoption workflows. Spanning military, apprenticeship, industry certification, and professional licensure fields. |
| 2026-03-20 | Progress Update | 288 cumulative credit recommendations; 281 adopted this year; 230 in progress through adoption workflow |