2.2  Faculty Discipline Workgroups

✔ On Track

Activity 2: Faculty Workgroups & Credit Recommendations  |  Goal 1  |  April 14, 2026

| Status | On Track |
| --- | --- |
| Progress | 44% |
| Lead | ASCCC / Calvin Klein Gloria |
| Budget | Included in 2.1 (ASCCC Pathways to Credit (V0718)) |
| KPI Current | 11 Cumulative discipline faculty workgroups active |
| 2030 Goal | 25 |
| 2030 Stretch | 36 |
| 25-26 | 11/6 |
| 26-27 | 11/15 |
| 27-28 | 11/19 |
| 28-29 | 11/22 |
| 29-30 | 11/25 |

## Description

Faculty and industry workgroups are convened to make statewide credit recommendations.

## Latest Update

Date: 2026-04-07

11 workgroups convened spanning high-demand fields; 101 credential exhibits documented

## Workplan Notes

11 of 25 target statewide faculty workgroups convened, recommending CPL for credentials and military training across high-demand disciplines. 40 disciplines planned by 2030.

## Milestones

2025-26: 11 of 25 workgroups active; June 2026: Additional disciplines onboarded

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 11 workgroups convened spanning high-demand fields; 101 credential exhibits documented |
| 2026-04-07 | Workplan | 11 of 25 target statewide faculty workgroups convened, recommending CPL for credentials and military training across high-demand disciplines. 40 disciplines planned by 2030. |
| 2026-03-20 | Progress Update | 11 workgroups convened spanning high-demand fields; 101 credential exhibits documented |