3.1.2  CPL Offers & Awards Tracking

✔ Goal Met  ★ Stretch Met

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 85% |
| Lead | Samuel Lee / Crystal Nasio |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 22,149 cumulative veterans and service members served with CPL |
| 2030 Goal | 70,000 |
| 2030 Stretch | 85,000 |
| 25-26 | 22,149/30,000 |
| 26-27 | 22,149/40,000 |
| 27-28 | 22,149/50,000 |
| 28-29 | 22,149/60,000 |
| 29-30 | 22,149/70,000 |

## Description

Of the 250,000, expand equitable CPL access to 70,000 cumulative veterans and service members by 2030.

## Latest Update

Date: 2026-04-08

Cumulative veterans and service members served with CPL exceeded 2025-26 annual target

## Workplan Notes

21552 cumulative veterans and service members offered some form of CPL as of 4/7/2026 per the CPL Dashboard. Short of the ambitious Veteran Sprint Goal of 30,000 but on track to achieve the target by June 30, 2026.

## Milestones

2025-26 target: 35,000 (exceeded at 42,958); 2030: 250,000

## Update Log

2 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative veterans and service members served with CPL exceeded 2025-26 annual target |
| 2026-04-08 | Workplan | 21552 cumulative veterans and service members offered some form of CPL as of 4/7/2026 per the CPL Dashboard. Short of the ambitious Veteran Sprint Goal of 30,000 but on track to achieve the target by June 30, 2026. |