3.1  CPL Offers & Awards Tracking

✔ Goal Met  ★ Stretch Met

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 85% |
| Lead | Samuel Lee / Crystal Nasio |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 43,630 cumulative Californians served with CPL awards |
| 2030 Goal | 250,000 |
| 2030 Stretch | 380,000 |
| 25-26 | 43,630/40,000 |
| 26-27 | 43,630/90,000 |
| 27-28 | 43,630/140,000 |
| 28-29 | 43,630/196,000 |
| 29-30 | 43,630/250,000 |

## Description

Expand equitable CPL access to 250,000 Californians (cumulative all populations), including military, working adults, apprentices, and all those with prior learning.

## Latest Update

Date: 2026-04-08

Cumulative students served with CPL exceeded 2025-26 annual target

## Workplan Notes

43630 cumulative students offered some form of CPL as of 4/7/2026 per the CPL Dashboard. Exceeds the 2025-26 annual target of 40,000.

## Milestones

2025-26 target: 35,000 (exceeded at 42,958); 2030: 250,000

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative students served with CPL exceeded 2025-26 annual target |
| 2026-04-08 | Workplan | 43630 cumulative students offered some form of CPL as of 4/7/2026 per the CPL Dashboard. Exceeds the 2025-26 annual target of 40,000. |
| 2026-04-07 | Progress Update | 42,958 cumulative students with CPL awards; exceeded 2025-26 annual target of 35,000 |
| 2026-04-07 | Workplan | 42,958 cumulative students offered some form of CPL as of 3/20/2026 per the CPL Dashboard. Exceeds the 2025-26 annual target of 35,000. Includes military (20,845), non-military (22,045), and apprentices (692). |
| 2026-03-20 | Progress Update | 42,958 cumulative students with CPL awards; exceeded 2025-26 annual target of 35,000 |