3.2  CPL Units Transcription

✔ Goal Met  ★ Stretch Met

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 80% |
| Lead | Samuel Lee / Crystal Nasio |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | 96,449 transcripted CPL units |
| 2030 Goal | 750,000 |
| 2030 Stretch | 930,000 |
| 25-26 | 96,449/90,000 |
| 26-27 | 96,449/195,000 |
| 27-28 | 96,449/315,000 |
| 28-29 | 96,449/450,000 |
| 29-30 | 96,449/750,000 |

## Description

Ensure CPL units are accurately reflected on student records

## Latest Update

Date: 2026-04-08

Cumulative transcripted CPL units exceeds 2025-26 annual target of 85,000

## Workplan Notes

96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units.

## Milestones

2025-26 target: 85,000 (exceeded at 96,449); training on transcription procedures ongoing

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative transcripted CPL units exceeds 2025-26 annual target of 85,000 |
| 2026-04-08 | Workplan | 96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units. |
| 2026-04-07 | Progress Update | 96,449 transcripted CPL units; exceeds 2025-26 annual target of 85,000 |
| 2026-04-07 | Workplan | 96,449 transcripted CPL units recorded. Exceeds the 2025-26 annual target of 85,000. Includes military (12,000), non-military (82,000), and apprentice (6,000) units. |
| 2026-03-20 | Progress Update | 96,449 transcripted CPL units; exceeds 2025-26 annual target of 85,000 |