3.3  Institutional Participation

✔ Goal Met  ★ Stretch Met

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 73% |
| Lead | Crystal Nasio |
| Budget | $5,900,000 (CPL Infrastructure & Scaling ($15M one-time)) |
| KPI Current | 84 colleges at active participation threshold |
| 2030 Goal | 100 |
| 2030 Stretch | 130 |
| 25-26 | 84/50 |
| 26-27 | 84/60 |
| 27-28 | 84/80 |
| 28-29 | 84/90 |
| 29-30 | 84/100 |

## Description

Colleges. IHLs, and agencies throughout the system and state actively use the MAP CPL infrastructure to offer, document and award CPL.

## Latest Update

Date: 2026-04-08

Cumulative institutions meet active threshold; 114 received $50K grants; 53 at implementation stage, 13 showing growth

## Workplan Notes

84 colleges meet the active threshold (10+ students and 5+ articulations). 114 of 115 credit colleges and 4 noncredit campuses received $50,000 CPL implementation funding. 53 at implementation stage, 13 showing growth.

## Milestones

2025-26 target: 50 colleges active (exceeded at 84); 114 colleges funded; 53 at implementation stage

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative institutions meet active threshold; 114 received $50K grants; 53 at implementation stage, 13 showing growth |
| 2026-04-08 | Workplan | 84 colleges meet the active threshold (10+ students and 5+ articulations). 114 of 115 credit colleges and 4 noncredit campuses received $50,000 CPL implementation funding. 53 at implementation stage, 13 showing growth. |
| 2026-04-07 | Progress Update | 84 colleges meet active threshold; 114 received $50K grants; 53 at implementation stage, 13 showing growth |
| 2026-04-07 | Workplan | 84 colleges meet the active threshold (10+ students and 5+ articulations). 114 of 115 credit colleges and 4 noncredit campuses received $50,000 CPL implementation funding. 53 at implementation stage, 13 showing growth. |
| 2026-03-20 | Progress Update | 84 colleges meet active threshold; 114 received $50K grants; 53 at implementation stage, 13 showing growth |