3.4  Student Impact Rate Survey

○ Not Started

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | Not Started |
| --- | --- |
| Progress | 5% |
| Lead | Terence Nelson |
| Budget | Included in 1.1 (MAP Team Operations (GFA0164)) |
| KPI Current | N/A |
| 2030 Goal | 0.9 |
| 2030 Stretch | 0.9 |
| 25-26 | —/0.7 |
| 26-27 | —/0.8 |
| 27-28 | —/0.8 |
| 28-29 | —/0.8 |
| 29-30 | —/0.9 |

## Description

Deploy CPL student impact survey tool within Student Portal to measure career and educational outcomes

## Latest Update

Date: 2026-04-07

Survey tool not yet deployed; infrastructure under development; will launch with Student Portal

## Workplan Notes

Survey tool is not yet deployed. Data collection infrastructure is still under development. The CPL Student Portal launching April 2026 will include the embedded student impact survey for first-ever systematic collection.

## Milestones

April 2026: Survey tool embedded in Student Portal launch

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Survey tool not yet deployed; infrastructure under development; will launch with Student Portal |
| 2026-04-07 | Workplan | Survey tool is not yet deployed. Data collection infrastructure is still under development. The CPL Student Portal launching April 2026 will include the embedded student impact survey for first-ever systematic collection. |
| 2026-03-20 | Progress Update | Survey tool not yet deployed; infrastructure under development; will launch with Student Portal |