3.5  Student Stories

✔ On Track

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | On Track |
| --- | --- |
| Progress | 64% |
| Lead | Crystal Nasio |
| Budget | Included in 1.1 (MAP Team Operations (GFA0164)) |
| KPI Current | 32 student stories published |
| 2030 Goal | 200 |
| 2030 Stretch | 230 |
| 25-26 | 32/30 |
| 26-27 | 32/60 |
| 27-28 | 32/120 |
| 28-29 | 32/160 |
| 29-30 | 32/200 |

## Description

Publish CPL student stories on MAP website; develop AI-assisted story capture tool

## Latest Update

Date: 2026-04-08

Cumulative student stories published on My CPL Story and MAP AI-assisted capture tool--in development

## Workplan Notes

32 student stories published on the My CPL Story section of the MAP website. AI-assisted student story capture tool is in development for June 2026 production release.

## Milestones

June 2026: AI-assisted story capture tool production release; target: 50 published stories

## Update Log

5 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | Cumulative student stories published on My CPL Story and MAP AI-assisted capture tool--in development |
| 2026-04-08 | Workplan | 32 student stories published on the My CPL Story section of the MAP website. AI-assisted student story capture tool is in development for June 2026 production release. |
| 2026-04-07 | Progress Update | 32 student stories published on My CPL Story; AI-assisted capture tool in development |
| 2026-04-07 | Workplan | 32 student stories published on the My CPL Story section of the MAP website. AI-assisted student story capture tool is in development for June 2026 production release. |
| 2026-03-20 | Progress Update | 32 student stories published on My CPL Story; AI-assisted capture tool in development |