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3.8  MIS Data Reconciliation
↑ In Progress
Activity 3: Scale CPL Access, Awards, and Procedures  |  Goal 2  |  October 29, 2026
	Status
	In Progress

	Progress
	25%

	Lead
	CO MIS / MAP Team

	Budget
	Included in operations (CPL Operations (ongoing $5M))

	KPI Current
	N/A

	2030 Goal
	N/A

	2030 Stretch
	N/A

	25-26
	—/—

	26-27
	—/—

	27-28
	—/—

	28-29
	—/—

	29-30
	—/—


Description
Align MAP and MIS CPL data for consistent systemwide reporting; target full alignment by 2027
Latest Update
Date: 2026-10-15
Work has progressed from scoping into active reconciliation tasks including source tracking, student-status rules, bulk-upload validation, veteran/active-duty classifications, and college-level outlier review, with current priority on validating MAP and MIS figures before recognition or funding reporting. A significant slow-down in CO data sharing has decreased velocity, prompting MAP to initiate college workgroups discussing transcription and MIS reporting best practices. Procedures and supporting tools are delayed due to the data sharing, though best practices and effort on the college side still slated for completion by end of 2026.
Workplan Notes
MIS and MAP reconciliation procedures and tools to support data integrity and interoperability, scheduled for release at end of 2026. MIS Data Element Dictionary SY domain was revised this academic year.
Milestones
End of 2026: MIS and MAP reconciliation procedures and tools released
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