4.1.2  Apprenticeship Sprint

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 1  |  April 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 35% |
| Lead | Terence Nelson |
| Budget | $1,345,236 (MAP Addendum - N2N Lightleap AI) |
| KPI Current | 1 Count of sprint goal progress achieved |
| 2030 Goal | 5 |
| 2030 Stretch | 8 |
| 25-26 | 1/1 |
| 26-27 | 1/2 |
| 27-28 | 1/3 |
| 28-29 | 1/4 |
| 29-30 | 1/5 |

## Description

Document every recent/current CCC apprentice by trade, union, CPL awarded, program, and workforce region

## Latest Update

Date: 2026-04-08

678 apprentice students documented; 6,000 units; DAS partnership active; Cal-JAC early partner for 14,000 first responders

## Workplan Notes

Apprenticeship Sprint: 678 apprentice students documented with 6,000 CPL units. DAS partnership active. Cal-JAC early partner for 14,000 first responder trainees. ~1,000 LAUNCH Network records expected Spring 2026.

## Milestones

Spring 2026: ~1,000 LAUNCH Network apprenticeship records uploaded; DAS data integration for 30,000+ records

## Update Log

2 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | 678 apprentice students documented; 6,000 units; DAS partnership active; Cal-JAC early partner for 14,000 first responders |
| 2026-04-08 | Workplan | Apprenticeship Sprint: 678 apprentice students documented with 6,000 CPL units. DAS partnership active. Cal-JAC early partner for 14,000 first responder trainees. ~1,000 LAUNCH Network records expected Spring 2026. |