4.1.4  29 Palms Marine Corps Base Demo

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 1  |  April 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 20% |
| Lead | Calvin Klein Gloria |
| Budget | Included in 1.1 (MAP Team Operations (GFA0164)) |
| KPI Current | 0 MOS pathways developed |
| 2030 Goal | 5 |
| 2030 Stretch | 8 |
| 25-26 | 0/1 |
| 26-27 | 0/2 |
| 27-28 | 0/3 |
| 28-29 | 0/4 |
| 29-30 | 0/5 |

## Description

Partnership with Twentynine Palms MCAGCC + Copper Mountain College; develop CPL pathways for 42 MOS trained at base

## Latest Update

Date: 2026-04-08

New demonstration project launched; coordinated outreach with Cal VET and military education center underway

## Workplan Notes

29 Palms Demo: New demonstration project launched. Developing CPL pathways for 42 Military Occupational Specialties (MOS) trained at MCAGCC. Coordinated outreach with Cal VET and military education center underway.

## Milestones

July 2026: Initial outcomes; March 2027: Scalable model for replication across 34 CA military bases

## Update Log

2 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | New demonstration project launched; coordinated outreach with Cal VET and military education center underway |
| 2026-04-08 | Workplan | 29 Palms Demo: New demonstration project launched. Developing CPL pathways for 42 Military Occupational Specialties (MOS) trained at MCAGCC. Coordinated outreach with Cal VET and military education center underway. |