4.1  Sprints and Projects

✔ On Track

Activity 4: Sprints, Projects & Partnerships  |  Goal 1  |  April 14, 2026

| Status | On Track |
| --- | --- |
| Progress | 65% |
| Lead | Calvin Klein Gloria |
| Budget | Included in 1.1 (MAP Team Operations (GFA0164)) |
| KPI Current | 8 Count of sprints, projects underway |
| 2030 Goal | 15 |
| 2030 Stretch | 23 |
| 25-26 | 8/1 |
| 26-27 | 8/4 |
| 27-28 | 8/7 |
| 28-29 | 8/11 |
| 29-30 | 8/15 |

## Description

CPL sprints, pilot projects, CPL outreach, and demonstration projects are supported with new CPL opportunities and resources.

## Latest Update

Date: 2026-04-08

3 Sprints underway: Veteran, Apprenticeship, and Statewide Adoptions; 1 new Military Base demonstration project underway;  and several projects underway.

## Workplan Notes

Veteran Sprint: 20,991 JSTs uploaded (62% of ~34,000 target). 75 colleges awarding basic training credit (up from ~15% baseline). 679 unique ACE credit recommendations covered. $163M estimated savings.

## Milestones

Goal 1: 100 colleges upload 5+ JSTs (78 of 100); Goal 2: 75 colleges award basic training credit; Goal 3: 58 colleges with articulated ACE recs

## Update Log

2 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-08 | Progress Update | 3 Sprints underway: Veteran, Apprenticeship, and Statewide Adoptions; 1 new Military Base demonstration project underway; and several projects underway. |
| 2026-04-08 | Workplan | Veteran Sprint: 20,991 JSTs uploaded (62% of ~34,000 target). 75 colleges awarding basic training credit (up from ~15% baseline). 679 unique ACE credit recommendations covered. $163M estimated savings. |