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4.2.1  AI Apprenticeship CPL Tools
↑ In Progress
Activity 4: Sprints, Projects & Partnerships  |  Goal 1; Goal 2  |  October 29, 2026
	Status
	In Progress

	Progress
	30%

	Lead
	Terence Nelson

	Budget
	$1,400,000 (MAP Addendum - N2N Lightleap AI + $54,764 pilot)

	KPI Current
	N/A

	How it is counted
	Outcomes are identified in the project contract and counted when accomplished.

	2030 Goal
	0

	2030 Stretch
	0

	25-26
	—/2

	26-27
	—/4

	27-28
	—/0

	28-29
	—/0

	29-30
	—/0


Description
AI tools for apprenticeship/journey worker CPL, degree-progress reports, and outreach; pilot with construction/electrician trades
Latest Update
Date: 2026-10-15
The N2N/Prism pilot has expanded from Santiago Canyon to American River College and additional statewide use cases, achieving 93–95% course-mapping accuracy with human review, petition generation, and approved CPL data push to MAP. PeopleSoft integration is planned for American River, and MAP is evaluating complementary competency-reconstruction tools for apprenticeship-to-course comparison while prioritizing reliable implementation at initial colleges.
Workplan Notes
AI apprenticeship CPL tools Phase 1 in progress with construction and electrician trades at Santiago Canyon College and Norco College. Proof-of-concept pilot funded ($54,764). Phase 2 will scale statewide.
Milestones
Phase 1: Construction and electrician trades at SCC and Norco; Phase 2: Scale statewide with trade partners
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