4.3  Technical Assistance & Training

✔ Goal Met  ★ Stretch Met

Activity 4: Sprints, Projects & Partnerships  |  Goal 1; Goal 3  |  April 14, 2026

| Status | Stretch Met |
| --- | --- |
| Progress | 85% |
| Lead | Crystal Nasio |
| Budget | $233,589 (CCC Foundation Regional Trainings) |
| KPI Current | 25 trainings delivered |
| 2030 Goal | 60 |
| 2030 Stretch | 96 |
| 25-26 | 25/10 |
| 26-27 | 25/23 |
| 27-28 | 25/35 |
| 28-29 | 25/48 |
| 29-30 | 25/60 |

## Description

Deliver local, regional, and statewide CPL training; 25+ events reaching 1,000+ participants

## Latest Update

Date: 2026-04-07

25 trainings delivered incl. 6th Annual CPL Summit and 4 Regional Trainings; 1,000+ staff/faculty/admins trained

## Workplan Notes

25 trainings delivered including the 6th Annual CPL Summit and 4 CPL Regional Training Workshops. Over 1,000 staff, faculty, and administrators trained. Individual technical assistance and office hours ongoing.

## Milestones

2025-26: Remaining regional workshops; focus on newly-funded colleges

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | 25 trainings delivered incl. 6th Annual CPL Summit and 4 Regional Trainings; 1,000+ staff/faculty/admins trained |
| 2026-04-07 | Workplan | 25 trainings delivered including the 6th Annual CPL Summit and 4 CPL Regional Training Workshops. Over 1,000 staff, faculty, and administrators trained. Individual technical assistance and office hours ongoing. |
| 2026-03-20 | Progress Update | 25 trainings delivered incl. 6th Annual CPL Summit and 4 Regional Trainings; 1,000+ staff/faculty/admins trained |