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4.4.1  VRC CPL Module Revision
↑ In Progress
Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 29, 2026
	Status
	In Progress

	Progress
	45%

	Lead
	Beth Kay / Crystal Nasio

	Budget
	Included in 4.3 (CCC Foundation Regional Trainings)

	KPI Current
	N/A

	How it is counted
	Each training module in production is counted

	2030 Goal
	4

	2030 Stretch
	8

	25-26
	—/0

	26-27
	—/6

	27-28
	—/4

	28-29
	—/4

	29-30
	—/4


Description
Vision Resource Center technical assistance modules focused on CPL policy, procedure, resources, tools, integrations, opportunities for all constituents.
Latest Update
Date: 2026-10-15
Continued progress on CPL Vision Resource Center module revision: 10 of 14 modules (71%) are finalized, with 8 submitted to VRC, 2 awaiting handoff, and 4 in development or review. Current focus is on completing remaining reviews, incorporating subject matter expert feedback, and submitting outstanding modules.
Workplan Notes
VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026.
Milestones
Feb-Apr 2026: Content development; May-Jun: Revisions and final packaging
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