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4.6  Sustainable Funding
↑ In Progress
Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  October 29, 2026
	Status
	In Progress

	Progress
	40%

	Lead
	Samuel Lee / James Todd

	Budget
	$89,000,000 (5-yr plan) (All CPL funding sources)

	KPI Current
	3 distributed to colleges ($)

	2030 Goal
	6

	2030 Stretch
	10

	25-26
	3/1

	26-27
	3/3

	27-28
	3/4

	28-29
	3/5

	29-30
	3/6


Description
Advance improvements in sustainable funding models and development of external funding to support ongoing CPL work.
Latest Update
Date: 2026-07-23
SB 135 and AB 135 were enacted, providing $7 million in ongoing funding for CPL Initiative operations, technical assistance, faculty workgroups, technology development, partnerships, and intersegmental collaboration, plus $35 million to support college awards based on CPL outcomes, projects, and innovations. The Chancellor's Office has drafted a two-year college funding model, with finalization expected in August 2026, field deployment in October 2026, and first disbursements planned for November or December 2026. Link to bills: https://legiscan.com/CA/text/AB135/id/3044016
Workplan Notes
$50,000 distributed to 114 of 115 credit colleges and 4 noncredit campuses for CPL implementation. $6M one-time fully allocated. 2026 advocacy active for $2M ongoing + $35M one-time appropriation.
Milestones
2026-27: $24.7M budgeted (if proposed funds approved); 2029-30: $9.1M; Total: $89M
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