5.1  AI-Ready California Demonstration

○ Not Started

Activity 4: Sprints, Projects & Partnerships  |  Goal 1; Goal 3  |  April 14, 2026

| Status | Not Started |
| --- | --- |
| Progress | 5% |
| Lead | Samuel Lee |
| Budget | $7,000,000 (Proposed: AI-Ready CA ($7M)) |
| KPI Current | 0 districts onboarded |
| 2030 Goal | 4 |
| 2030 Stretch | N/A |
| 25-26 | 0/— |
| 26-27 | 0/— |
| 27-28 | 0/— |
| 28-29 | 0/— |
| 29-30 | 0/4 |

## Description

$7M two-year project: CPL-embedded AI workforce pathway from HS dual enrollment through AS to BAS-ASIO baccalaureate across 4 districts

## Latest Update

Date: 2026-04-07

Project proposal developed; 4 demo districts identified; BAS-ASIO curriculum in design; contingent on funding

## Workplan Notes

AI-Ready California: Proposed $7M two-year demonstration. 4 demo districts identified (RCCD, SDCCD, LACCD, SBCCD). BAS-ASIO curriculum in design. Contingent on funding approval.

## Milestones

Fall 2025: MOUs and staffing; Spring 2026: AI cert CPL recs drafted; Fall 2026: Dual enrollment launch at 8+ HS

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Project proposal developed; 4 demo districts identified; BAS-ASIO curriculum in design; contingent on funding |
| 2026-04-07 | Workplan | AI-Ready California: Proposed $7M two-year demonstration. 4 demo districts identified (RCCD, SDCCD, LACCD, SBCCD). BAS-ASIO curriculum in design. Contingent on funding approval. |
| 2026-03-20 | Progress Update | Project proposal developed; 4 demo districts identified; BAS-ASIO curriculum in design; contingent on funding |