5.2  AI Certification-to-Course Matching

✔ On Track

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 2  |  April 14, 2026

| Status | On Track |
| --- | --- |
| Progress | 55% |
| Lead | Terence Nelson |
| Budget | Included in 2.3 (AI Skills to Course Alignment (V0515)) |
| KPI Current | 117 industry certifications matched |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | 117/— |
| 26-27 | 117/— |
| 27-28 | 117/— |
| 28-29 | 117/— |
| 29-30 | 117/— |

## Description

AI-assisted matching of 117 industry certifications to CCC courses across priority sectors; Phase 2 beta expanding pool

## Latest Update

Date: 2026-04-07

Phase 1 complete covering 117 industry certifications in priority sectors; Phase 2 beta underway

## Workplan Notes

AI cert-to-course matching Phase 1 complete covering 117 industry certifications in priority sectors. Phase 2 beta expanding certification pool. Production release planned June 2026.

## Milestones

Phase 1 complete: 117 certs covered; June 2026: Phase 2 production release expanding cert pool

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Phase 1 complete covering 117 industry certifications in priority sectors; Phase 2 beta underway |
| 2026-04-07 | Workplan | AI cert-to-course matching Phase 1 complete covering 117 industry certifications in priority sectors. Phase 2 beta expanding certification pool. Production release planned June 2026. |
| 2026-03-20 | Progress Update | Phase 1 complete covering 117 industry certifications in priority sectors; Phase 2 beta underway |