5.3  AI Apprenticeship CPL Tools

↑ In Progress

Activity 1: AI-Enhanced CPL Infrastructure  |  Goal 1; Goal 2  |  April 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 30% |
| Lead | Terence Nelson |
| Budget | $1,400,000 (MAP Addendum - N2N Lightleap AI + $54,764 pilot) |
| KPI Current | N/A |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | —/— |
| 26-27 | —/— |
| 27-28 | —/— |
| 28-29 | —/— |
| 29-30 | —/— |

## Description

AI tools for apprenticeship/journey worker CPL, degree-progress reports, and outreach; pilot with construction/electrician trades

## Latest Update

Date: 2026-04-07

Phase 1 in progress; proof-of-concept pilot funded ($54,764); $1.35M project funding from $6M appropriation

## Workplan Notes

AI apprenticeship CPL tools Phase 1 in progress with construction and electrician trades at Santiago Canyon College and Norco College. Proof-of-concept pilot funded ($54,764). Phase 2 will scale statewide.

## Milestones

Phase 1: Construction and electrician trades at SCC and Norco; Phase 2: Scale statewide with trade partners

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Phase 1 in progress; proof-of-concept pilot funded ($54,764); $1.35M project funding from $6M appropriation |
| 2026-04-07 | Workplan | AI apprenticeship CPL tools Phase 1 in progress with construction and electrician trades at Santiago Canyon College and Norco College. Proof-of-concept pilot funded ($54,764). Phase 2 will scale statewide. |
| 2026-03-20 | Progress Update | Phase 1 in progress; proof-of-concept pilot funded ($54,764); $1.35M project funding from $6M appropriation |