5.5  VRC CPL Module Revision

↑ In Progress

Activity 4: Sprints, Projects & Partnerships  |  Goal 3  |  April 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 45% |
| Lead | Beth Kay / Crystal Nasio |
| Budget | Included in 4.3 (CCC Foundation Regional Trainings) |
| KPI Current | N/A |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | —/— |
| 26-27 | —/— |
| 27-28 | —/— |
| 28-29 | —/— |
| 29-30 | —/— |

## Description

Rewrite and expand Virtual Resource Center CPL training modules with CCCF/Success Center

## Latest Update

Date: 2026-04-07

Review and gap analysis complete; content development phase underway

## Workplan Notes

VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026.

## Milestones

Feb-Apr 2026: Content development; May-Jun: Revisions and final packaging

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | Review and gap analysis complete; content development phase underway |
| 2026-04-07 | Workplan | VRC CPL Module revision: Review and gap analysis complete. Content development phase underway. Final packaging targeted May-June 2026. |
| 2026-03-25 | Progress Update | Review and gap analysis complete; content development phase underway |