5.7  MIS Data Reconciliation

↑ In Progress

Activity 3: CPL Data Infrastructure  |  Goal 2  |  April 14, 2026

| Status | In Progress |
| --- | --- |
| Progress | 25% |
| Lead | CO MIS / MAP Team |
| Budget | Included in operations (CPL Operations (ongoing $5M)) |
| KPI Current | N/A |
| 2030 Goal | N/A |
| 2030 Stretch | N/A |
| 25-26 | —/— |
| 26-27 | —/— |
| 27-28 | —/— |
| 28-29 | —/— |
| 29-30 | —/— |

## Description

Align MAP and MIS CPL data for consistent systemwide reporting; target full alignment by 2027

## Latest Update

Date: 2026-04-07

MIS Data Element Dictionary SY domain revised; training sessions held; Common Cloud integration planned

## Workplan Notes

MIS and MAP reconciliation procedures and tools to support data integrity and interoperability, scheduled for release at end of 2026. MIS Data Element Dictionary SY domain was revised this academic year.

## Milestones

End of 2026: MIS and MAP reconciliation procedures and tools released

## Update Log

3 logged updates — newest first

| Date | Type | Note |
| --- | --- | --- |
| 2026-04-07 | Progress Update | MIS Data Element Dictionary SY domain revised; training sessions held; Common Cloud integration planned |
| 2026-04-07 | Workplan | MIS and MAP reconciliation procedures and tools to support data integrity and interoperability, scheduled for release at end of 2026. MIS Data Element Dictionary SY domain was revised this academic year. |
| 2026-03-20 | Progress Update | MIS Data Element Dictionary SY domain revised; training sessions held; Common Cloud integration planned |